CFDE Monthly Report February 2021		OT2 OD030544 	PI: Subramaniam

During this month, we accomplished the following:

1. Continued development of the C2M2 phase 0/1 submission

In our milestone issue 1.2. we have provided the required files for C2M2 tables concerning metabolomics data. In our milestone/issue 1.3.1., we have to provide the followings:

REFMET dictionary to provide names of all metabolites.
IDs to relate to other resources – PubChem, KEGG, HMDB, InchiKey.
Links to metabolite molecules database resource for each Metabolite. We submitted this information in an excel file. The first sheet has the information on the column names used in the second sheet (which contains the actual data).

2.  MetENP Appyter Development

We continue to work on the MetENP Appyter development and have ironed out format conversions from R to python. The Appyter is now active and will be submitted to GitHub.

2.  Co-leading a Working Group

We are initiating a new Working Group for clinical metadata framework and characterization across resources in collaboration with Drs. De Bono and Adam Resnick. Towards this we developed a draft below.

CFDE Clinical Metadata Working Group and Mission

Overall Goal

The CFDE Clinical Metadata WG was created based on a consensus that to enable discoverability and interoperability of data associated with human subjects, there is an absolute need for developing a minimal but comprehensive clinical metadata scheme. This scheme will be based on existing and accepted ontologies that the community has adopted.

Use Cases

We provide 2 use cases to motivate the goals of the Working Group.

- A clinician researcher is reviewing a 52-year-old female Type II diabetes patient who has been treated for 2 years with metformin. She wishes to identify key genes/functions altered in patients with similar demographic and dietary profile (dbGaP, Framingham study/TOPMED data) as well as identify metabolite differences associated with physiological phenotypes in similar patients (NMDR). She also wishes to see consequences for cardiovascular conditions in such patients (Dallas Heart Study, TEDDY data). Discoverability of such data will depend critically on availability of appropriate clinical metadata associated with each of the data resources.

- A researcher who works on enchondromatoses in children is interested in identifying using family/trios information genomic variants in these subjects and seek if the variant is associated with Ollier disease associated with skeletal dysplasia. There is WGS data on these trios in Gabriella Miller Kids First resource (dbGaP). There are also gene expression data in GEO on zone specific gene expression patterns in articular cartilage on 4 normal human donors. The researcher would like to seek if the genes associated with variants (including sequences of trios) are expressed differentially in the GEO resource. The study would be meaningful if the associated metadata associated with age, clinical conditions and other related information are available. What metadata would enable the cross-mapping?

CF data resources like Metabolomics Workbench, Kids First, HMP and others and other national data resources like TOPMED, TEDDY and Framingham and NIH resources like dbGaP offer unprecedented opportunity to biomedical researchers make new discoveries. However, discoverability of data in critically hinged on metadata associated with each study. To help the research community query these data in an integrative manner, we need to develop both a structured vocabulary, set of tools that translate formats across extant data, and a query engine that is biomedical researcher-friendly.

Proposal for Action

- Design a framework for defining minimal clinical metadata that will enable discoverability and interoperability across defined data sets.

- As a first step get each DCC to provide their current metadata schema and vocabulary.

- The Working Group should explore development of clinical metadata formats in dbGaP, TOPMED, TEDDY, and other defined large human subjects data projects.

- Draft a Schema for Clinical Profile.

- Unify Clinical & Non-Clinical Data Entities >> OWL-RDF.

- Explore of OBO and SnoMedCT would be adequate to represent CFDE clinical metadata requirements.

- Develop the requirements for a building a query interface.

- Design the elements required for API construction for interoperability.

- Discuss interactions with C2M2 and with other stakeholders.

- Develop documentation requirements for the minimal clinical metadata model.

Request from the CFDE CC team:

- The proposal for action listed above is appropriate. In particular the use cases mentioned require that all DCCs use a specific set of clinical metadata associated with their data and the vocabulary/terms deployed.

- Regarding the scope of data tied to clinical metadata, for data associated with you class of studies please articulate which data and API tools would be expected to be loaded into the C2M2 data model. For example, develop exemplars to show how data can be discovered using metadata objects from your resource.

- Identify examples of how your data can be interoperated with data from other DCCs using clinical metadata-based queries.